## Sheet1
Project Shortname | Project Name | Stream | Building Name | Building Type | Series | Output Tracking | Day/Date | Total Area m2 | Remarks (Free Form) | Grand Total m2 | (Aug) Produced (cumulative) | (Sept) Produced (cumulative) | (Oct) Produced (cumulative) | (Nov) Produced (cumulative) | (Dec) Produced (cumulative) | Total Produced | 2026-08-01 | 2026-08-02 | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-07 | 2026-08-08 | 2026-08-09 | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-16 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-22 | 2026-08-23 | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-29 | 2026-08-30 | 2026-08-31 | (Aug) Not Produce | (Sept) Not Produce | (Oct) Not Produce | (Nov) Not Produce | (Dec) Not Produce | Total not Produce | Reason (Not Produce)
AP24 | INDIA - Alekhya Property Developments - Adarsh Parkland Phase 2 Block 4 | 1 | Tower A | Typical | 1 | New | Normal |  |  | 200 | 100 |  |  |  |  | 200 | 2026-08-01: 50; 2026-08-14: 50; 2026-08-21: 50; 2026-08-25: 50
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
|  |  |  | Upper Lv 10 | 1 | New | Normal |  |  | 400 |  |  | 200 |  |  | 400
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
[5 empty] | 2 | New | Normal | [6 empty] | 200
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
|  | 2 | Tower B | Typical | 1 | New | Normal |  |  | 600 |  | 300 |  |  |  | 500
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
[5 empty] | 2 | New | Normal | [5 empty] | 200
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
AP24 | INDIA - Alekhya Property Developments - Adarsh Parkland Phase 2 Block 4 | 1 | Tower A | Typical | 1 | New | Normal | [8 empty] | 400
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
[5 empty] | 2 | New | Normal | [8 empty] | 300
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
[5 empty] | 3 | New | Normal | [8 empty] | 200
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
|  |  |  | Upper Lv 10 | 1 | New | Normal | [8 empty] | 100
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
[5 empty] | 2 | New | Normal | [8 empty] | 200
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
|  | 2 | Tower B | Typical | 1 | New | Normal | [8 empty] | 300
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
[5 empty] | 2 | New | Normal | [8 empty] | 400
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
|  |  |  | Upper Lv 10 | 1 | New | Normal | [8 empty] | 500
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
[5 empty] | 2 | New | Normal | [8 empty] | 300
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
EG23 | MALAYSIA - C N H Enterprise - EG23, 206 unit DSTH in Elmina City | 1 | Tower A | Typical | 1 | New | Normal |  |  | 100 |  |  |  | 50 |  | 200
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
[5 empty] | 2 | New | Normal | [6 empty] | 50
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
|  |  |  | Upper Lvl.10 | 1 | New | Normal |  |  | 100 |  |  |  | 50 |  | 100 | [34 empty] | 50 |  | 50
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
[5 empty] | 2 | New | Normal
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
[5 empty] | 3 | New | Normal
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
[5 empty] | 4 | New | Normal
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
|  |  |  | Upper lv.30 | 1 | New | Normal | [8 empty] | 200
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
[5 empty] | 2 | New | Normal | [8 empty] | 300
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
EG23 | MALAYSIA - C N H Enterprise - EG23, 206 unit DSTH in Elmina City | 1 | Tower A | Typical | 1 | New | Normal | [8 empty] | 400
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
[5 empty] | 2 | New | Normal | [8 empty] | 500
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
|  |  |  | Upper Lvl.10 | 1 | New | Normal | [8 empty] | 400
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
[5 empty] | 2 | New | Normal | [8 empty] | 300
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
[5 empty] | 3 | New | Normal | [8 empty] | 200
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
[5 empty] | 4 | New | Normal | [8 empty] | 100
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
|  |  |  | Upper lv.30 | 1 | New | Normal | [8 empty] | 200
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
[5 empty] | 2 | New | Normal | [8 empty] | 300
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
EG23 | MALAYSIA - C N H Enterprise - EG23, 206 unit DSTH in Elmina City | 1 | Tower A | Typical | 1 | New | Normal | [8 empty] | 400
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
[5 empty] | 2 | New | Normal | [8 empty] | 500
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
|  |  |  | Upper Lvl.10 | 1 | New | Normal | [8 empty] | 400
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
[5 empty] | 2 | New | Normal | [8 empty] | 300
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
[5 empty] | 3 | New | Normal | [8 empty] | 200
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
[5 empty] | 4 | New | Normal | [8 empty] | 100
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
|  |  |  | Upper lv.30 | 1 | New | Normal | [8 empty] | 200
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
[5 empty] | 2 | New | Normal | [8 empty] | 300
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
EG23 | MALAYSIA - C N H Enterprise - EG23, 206 unit DSTH in Elmina City | 1 | Tower A | Typical | 1 | New | Normal | [8 empty] | 400
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
[5 empty] | 2 | New | Normal | [8 empty] | 500
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
|  |  |  | Upper Lvl.10 | 1 | New | Normal | [8 empty] | 400
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
[5 empty] | 2 | New | Normal | [8 empty] | 300
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
[5 empty] | 3 | New | Normal | [8 empty] | 200
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
[5 empty] | 4 | New | Normal | [8 empty] | 100
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
|  |  |  | Upper lv.30 | 1 | New | Normal | [8 empty] | 200
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
[5 empty] | 2 | New | Normal | [8 empty] | 300
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
BFD4 | SINGAPORE - Wee Hur Construction - Bedok FD4-4 Blk Apartment | 1 | Tower A | Typical | 1 | New | Normal | [8 empty] | 400
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
[5 empty] | 2 | New | Normal | [8 empty] | 500
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
[5 empty] | 3 | New | Normal | [8 empty] | 400
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
|  |  |  | Upper Lvl.10 | 1 | New | Normal | [8 empty] | 300
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
|  | 2 | Tower B | Typical | 1 | New | Normal | [8 empty] | 200
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
[5 empty] | 2 | New | Normal | [8 empty] | 100
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
[5 empty] | 3 | New | Normal | [8 empty] | 200
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
BFD4 | SINGAPORE - Wee Hur Construction - Bedok FD4-4 Blk Apartment | 1 | Tower A | Typical | 1 | New | Normal | [8 empty] | 300
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
[5 empty] | 2 | New | Normal | [8 empty] | 400
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
[5 empty] | 3 | New | Normal | [8 empty] | 500
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
|  |  |  | Upper Lvl.10 | 1 | New | Normal | [8 empty] | 400
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
|  | 2 | Tower B | Typical | 1 | New | Normal | [8 empty] | 300
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
[5 empty] | 2 | New | Normal | [8 empty] | 200
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck
[5 empty] | 3 | New | Normal | [8 empty] | 100
Quick Deck
[6 empty] | Spec | Daily
[6 empty] | RF | Direct Daily Normal
Modify Daily Normal
Refurbish Daily Normal
Direct From RF Normal
Direct Daily QD
Refurbish Daily QD
Direct From RF QD
[6 empty] | New Stock | Daily
Quick Deck

## Sheet2
Project | Project Short Code | Remarks (Free Form) | Stream | Tower | Building Type | Output Tracking | Day/Date | Total Area m2 | Grand Total m2 | (Aug) Not Produce | (Sept) Not Produce | (Oct) Not Produce | (Nov) Not Produce | (Dec) Not Produce | Total not Processed | Reason (Not Processed) | 2026-08-01 | 2026-08-02 | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-07 | 2026-08-08 | 2026-08-09 | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-16 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-22 | 2026-08-23 | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-29 | 2026-08-30 | 2026-08-31
Project Alpha 1 | PA1 |  | 1 | 1 |  | New | Normal
Cumu
Quick Deck
Cumu
[6 empty] | Spec | Daily
Cumu
[6 empty] | RF | Daily Normal
Cumu
From RF Normal
Cumu RF
Daily QD
Cumu
From RF QD
Cumu RF
[6 empty] | New Stock | Daily
Cumu
Quick Deck
Cumu
Project Alpha 2 | PA2 |  | 1 | 1 |  | New | Normal
Cumu
Quick Deck
Cumu
[6 empty] | Spec | Daily
Cumu
[6 empty] | RF | Daily Normal
Cumu
From RF Normal
Cumu RF
Daily QD
Cumu
From RF QD
Cumu RF
[6 empty] | New Stock | Daily
Cumu
Quick Deck
Cumu
Project Alpha 3 | PA3 |  | 1 | 1 |  | New | Normal
Cumu
Quick Deck
Cumu
[6 empty] | Spec | Daily
Cumu
[6 empty] | RF | Daily Normal
Cumu
From RF Normal
Cumu RF
Daily QD
Cumu
From RF QD
Cumu RF
[6 empty] | New Stock | Daily
Cumu
Quick Deck
Cumu
Project Alpha 4 | PA4 |  | 1 | 1 |  | New | Normal
Cumu
Quick Deck
Cumu
[6 empty] | Spec | Daily
Cumu
[6 empty] | RF | Daily Normal
Cumu
From RF Normal
Cumu RF
Daily QD
Cumu
From RF QD
Cumu RF
[6 empty] | New Stock | Daily
Cumu
Quick Deck
Cumu
Project Alpha 5 | PA5 |  | 1 | 1 |  | New | Normal
Cumu
Quick Deck
Cumu
[6 empty] | Spec | Daily
Cumu
[6 empty] | RF | Daily Normal
Cumu
From RF Normal
Cumu RF
Daily QD
Cumu
From RF QD
Cumu RF
[6 empty] | New Stock | Daily
Cumu
Quick Deck
Cumu