## Sheet1
Project No. | Project Name | BD (Dropdown) | Building Name | sub Building Name | DCF (Normal/Complex - Dropdown) | Shell Plan Status | Shell Plan Start Date | Latest Revision | Latest Submission Date | Shell Plan Approved Date | Remarks (Shell Model Update / Correction / Client Changes, etc) - Free Form
25124 | INDIA - Alekhya Property Developments - Adarsh Parkland Phase 2 Block 4 | Person A | Tower A | Typical | Normal | approved | 2026-10-01 |  |  | 2026-11-01
|  |  |  | Upper lv.10 | Normal | approved | 2026-10-02 |  |  | 2026-11-02
|  | Person A | Tower B | Typical | Normal | approved | 2026-10-03 |  |  | 2026-11-03
|  |  |  | Upper lv.10 | Normal | approved | 2026-10-04 |  |  | 2026-11-04
26213 | MALAYSIA - C N H Enterprise - EG23, 206 unit DSTH in Elmina City | Person B | Tower A | Typical | Normal | approved | 2026-10-05 |  |  | 2026-11-05
|  |  |  | Upper lv.10 | Normal | approved | 2026-10-06 |  |  | 2026-11-06
|  |  |  | Upper lv.30 | Normal | in progress |  |  |  | 2026-11-07
25428 | SINGAPORE - Wee Hur Construction - Bedok FD4-4 Blk Apartment | Person C | Tower A | Typical | Normal | approved | 2026-10-08 |  |  | 2026-11-08
|  |  |  | Upper lv.10 | Normal | in progress |  |  |  | 2026-11-09
|  | Person C | Tower B | Typical | Normal | in progress |  |  |  | 2026-11-10