## Sheet1
Project No. (from shellplan column A) | Project Name (from shellplan column B) | BD (dropdown) (from shellplan column C) | stream (from bd column D) | Building Name (from shellplan column D) | (from shellplan column E) | DCF (dropdown) (from shellplan column F) | Formwork Design Status | start design date | estimated design completion date (should be date or tbc) | Actual Formwork Order Completion Date | design duration -time (auto calc) - by day | Total Quantity Ordered m2 | design remarks - free form | holing status (Completed/Not Completed/) -dropdown | holing start date | holing completion date | remarks -free form | accessories status dropdown (to start, ongoing, completed, on hold) | accessories start date | accessories completion date | remarks -free form
25124 | INDIA - Alekhya Property Developments - Adarsh Parkland Phase 2 Block 4 | Person A | 1 | Tower A | Typical | Normal | Completed | 2026-09-02 | Est 26/10 | 2026-01-13 | -232 | 4129.38 | Standard panel ordered (1/8) ; Tower B ordered (9/1 - 3876.58m2) ; Tower A ordered (13/1 - 4129.38m2) (INA) | Completed | 2026-10-05 | 2026-10-08 |  | Completed | 2026-10-08 | 2026-10-07
[5 empty] | Upper lv.10 | Normal | ongoing | 2026-09-03 |  | 2026-10-06 |  |  |  | Not Completed | 2026-10-06 | 2026-10-05 |  | Not Completed | 2026-10-05 | 2026-10-10
|  | Person A | 2 | Tower B | Typical | Normal | to start | 2026-09-04 |  | 2026-10-07 |  |  |  | Not Completed | 2026-10-07 | 2026-10-06 |  | Not Completed | 2026-10-06 | 2026-10-11
[5 empty] | Upper lv.10 | Normal | to start | 2026-09-05 |  | 2026-10-08 |  |  |  | Not Completed | 2026-10-08 | 2026-10-07 |  | Not Completed | 2026-10-07 | 2026-10-12
26213 | MALAYSIA - C N H Enterprise - EG23, 206 unit DSTH in Elmina City | Person B | 1 | Tower A | Typical | Normal | to start | 2026-09-05 |  | 2026-10-10 |  |  |  | Not Completed | 2026-10-10 | 2026-10-13 |  | Not Completed | 2026-10-13 | 2026-10-16
[5 empty] | Upper lv.10 | Normal | ongoing | 2026-09-06 |  | 2026-10-11 |  |  |  | Not Completed | 2026-10-11 | 2026-10-14 |  | Not Completed | 2026-10-14 | 2026-10-17
[5 empty] | Upper lv.30 | Normal | Completed | 2026-09-07 |  | 2026-10-12 | 1900-02-03 | 100.2 |  | Completed | 2026-10-12 | 2026-10-14 |  | Completed | 2026-10-14 | 2026-10-19
25428 | SINGAPORE - Wee Hur Construction - Bedok FD4-4 Blk Apartment | Person C | 1 | Tower A | Typical | Normal | Completed | 2026-09-04 |  | 2026-10-26 | 1900-02-20 | 110.3 |  | Completed | 2026-10-26 | 2026-10-31 |  | Completed | 2026-10-31 | 2026-11-05
[5 empty] | Upper lv.10 | Normal | Completed |  |  | 2026-10-28 |  |  |  | Completed | 2026-10-28 | 2026-11-01 |  | Completed | 2026-11-01 | 2026-11-06
|  | Person C | 2 | Tower B | Typical | Normal | Completed | 2026-09-04 |  | 2026-10-30 | 1900-02-24 | 110.3 |  | Completed | 2026-10-30 | 2026-11-02 |  | Completed | 2026-11-02 | 2026-11-08