## Sheet1
Project Shortname | Project Name | Stream | Level of Building Type | Total FmWk Quantity | (Aug) Dispatched (cumulative) | (Sept) Dispatched (cumulative) | (Oct) Dispatched (cumulative) | (Nov) Dispatched (cumulative) | (Dec) DIspatched (cumulative) | Total Dispatched | SCP Value MYR | POD | Delivery to Port | ETA POL | Rev ETD | Rev 2 ETD | Rev 3 ETD | Rev 4 ETD | Rev 5 ETD | Rev 6 ETD | Rev 7 ETD | ATD | Formwork Quantity Sailed (m2) | SCP Value Sailed MYR | Destination | Mode of Transport | Incoterms | 40ft/ctr | 20ft/ctr | 40ft/ctr | 20ft/ctr | Feeder Vessel / Mother Vessel | Total Cost | Per M2 | (Aug) Not Dispatch (cumulative) | (Sept) Not Dispatch (cumulative) | (Oct) Not Dispatch (cumulative) | (Nov) Not Dispatch (cumulative) | (Dec) Not Dispatch (cumulative) | Total not Dispatch | Reason (Not Dispatch) | Total not Dispatch | Reason (Not Dispatch)
AP24 | INDIA - Alekhya Property Developments - Adarsh Parkland Phase 2 Block 4 | 1 | Tower A | 200 |  |  |  | 100 | 100 | 200 | [15 empty] | Land | No delivery |  |  |  |  | HENG HUI 6 V.0FDI5W1MA | 18500.00 USD | 1.8802
[32 empty] | INTERASIA TRIBUTE V. W019 | 12900.00 USD | 5.9574
[32 empty] | XIN XU ZHOU - 236N | 1700.00 USD | 0
[22 empty] | 2026-11-09 | 200
|  | 2 | Tower B
AP24 | INDIA - Alekhya Property Developments - Adarsh Parkland Phase 2 Block 4 | 1 | Tower A
|  | 2 | Tower B | [22 empty] | DHL
EG23 | MALAYSIA - C N H Enterprise - EG23, 206 unit DSTH in Elmina City | 1 | Tower A
EG23 | MALAYSIA - C N H Enterprise - EG23, 206 unit DSTH in Elmina City | 1 | Tower A
EG23 | MALAYSIA - C N H Enterprise - EG23, 206 unit DSTH in Elmina City | 1 | Tower A
EG23 | MALAYSIA - C N H Enterprise - EG23, 206 unit DSTH in Elmina City | 1 | Tower A
BFD4 | SINGAPORE - Wee Hur Construction - Bedok FD4-4 Blk Apartment | 1 | Tower A
|  | 2 | Tower B | [22 empty] | Land
BFD4 | SINGAPORE - Wee Hur Construction - Bedok FD4-4 Blk Apartment | 1 | Tower A
|  | 2 | Tower B